## Sheet1
Week | Task | Lead Member | Team Support | Expected Output | Status (To Do / In Progress / Done)
1-2 | Finalize project plan, set SMART goals, divide responsibilities | Mani | All Members | Project outline, SMART goals, team plan | To Do
3-4 | Collect and document dataset (grades, attendance, engagement) | Mani | Nazir, Pranay | Clean structured dataset (documented) | To Do
5-6 | Data cleaning, preprocessing, and feature engineering | Nazir | Mani, Pranay | Final preprocessed dataset ready for analysis | To Do
7-8 | Exploratory Data Analysis (EDA) and visualizations | Pranay | Shabaz, Navya | EDA report and visual insights | To Do
9-10 | Model building, training, and evaluation | Shabaz | Pranay, Navya | Model performance report and code | To Do
11-12 | Dashboard creation, interpretation, and insights | Navya | Mani, Nazir | Dashboard and draft report | To Do
13 | Write individual reflective reports (draft) | All Members | All Members | Individual reflective report draft | To Do
14 | Prepare and rehearse group presentation | All Members | All Members | Final presentation slides and rehearsal notes | To Do